## Dashboard
PureTask Implementation Tracking — Dashboard
Document 16 — Status of all CHG items from Doc 15 Lovable Implementation Brief
Status Summary
Status | Count | % of Total
Not Started | 90 | 100%
In Progress | 0 | 0%
Blocked | 0 | 0%
Done | 0 | 0%
Verified | 0 | 0%
Total | 90 | 100%
Priority Breakdown
Priority | Total | Done + Verified | % Complete
P0 | 62 | 0 | 0%
P1 | 25 | 0 | 0%
P2 | 3 | 0 | 0%
P3 | 0 | 0 | 0%
Progress by Section
Section | Total Items | Done | Verified | % Complete
1. Foundation | 10 | 0 | 0 | 0%
10. SMS Logic | 3 | 0 | 0 | 0%
11. Trust & Safety | 7 | 0 | 0 | 0%
12. Reviews | 1 | 0 | 0 | 0%
13. Accessibility | 7 | 0 | 0 | 0%
14. Mobile | 5 | 0 | 0 | 0%
15. Admin | 6 | 0 | 0 | 0%
2. Global UI | 4 | 0 | 0 | 0%
3. Legal Pages | 10 | 0 | 0 | 0%
4. Client Signup | 3 | 0 | 0 | 0%
5. Pro Signup | 12 | 0 | 0 | 0%
6. Booking Flow | 4 | 0 | 0 | 0%
7. Payment | 5 | 0 | 0 | 0%
8. Cancellation | 6 | 0 | 0 | 0%
9. Account Settings | 7 | 0 | 0 | 0%
★ CRITICAL ITEMS (must be Verified before public launch)
CHG-046 | STANDALONE FCRA Disclosure — Gilberg-compliant (single page, no other consent on it)
CHG-045 | Standalone Pro IC Agreement clickwrap (NOT bundled with ToS)
CHG-131 | SMS sending wrapper enforcing TCPA + FTSA quiet hours
CHG-001 | consent_records table immutability (no UPDATE/DELETE permissions)
CHG-006 | sms_consent_records 5-year retention
CHG-013 | GPC signal honored as CCPA opt-out
CHG-082 | Stripe Connect Express agent-of-payee architecture (no PureTask-held funds)
CHG-148 | Pre-Adverse Action Notice with 5-business-day wait window

## Items
CHG ID | Section | Title | Priority | Status | Owner | Dependencies | Acceptance Notes | Date Started | Date Completed | Date Verified | Lovable Session | Blocker / Notes
CHG-001 | 1. Foundation | Database schema: consent_records table | P0 | Not Started | Lovable | — | Audit-immutable consent record table for every clickwrap acceptance
CHG-002 | 1. Foundation | Database schema: legal_documents table | P0 | Not Started | Lovable | — | Versioned legal document storage with current-version constraint
CHG-003 | 1. Foundation | Database schema: user profile additions | P0 | Not Started | Lovable | CHG-001 | Add age, state, account_status, marketing opt-ins, CCPA opt-out, arbitration opt-out fields
CHG-004 | 1. Foundation | Database schema: pro_credentials table | P0 | Not Started | Lovable | CHG-003 | Encrypted credential storage for business license / EIN / COI
CHG-005 | 1. Foundation | Database schema: background_checks table | P0 | Not Started | Lovable | CHG-003 | Status tracking for Checkr workflow; no raw report content
CHG-006 | 1. Foundation | Database schema: sms_consent_records table | P0 | Not Started | Lovable | CHG-003 | TCPA-compliant SMS consent records; 5-year retention
CHG-007 | 1. Foundation | Database schema: audit_log table | P0 | Not Started | Lovable | — | Append-only audit log for PII access, admin actions, consent changes
CHG-008 | 1. Foundation | Environment variables setup | P0 | Not Started | Nathan | — | Stripe, Checkr, Twilio, OneSignal, email, compliance contacts, OFAC keys
CHG-009 | 1. Foundation | Install required dependencies | P0 | Not Started | Lovable | — | Stripe, Supabase, Twilio, Resend, Checkr, Zod, react-hook-form, date-fns-tz
CHG-010 | 1. Foundation | Constants file: legal & policy values | P0 | Not Started | Lovable | — | Hard limits and policy constants in lib/legal-constants.ts
CHG-011 | 2. Global UI | Site footer with legal links | P0 | Not Started | Lovable | CHG-010 | Footer on every page with Do Not Sell, Limit SPI, legal page links
CHG-012 | 2. Global UI | Cookie consent banner | P0 | Not Started | Lovable | CHG-001, CHG-013 | First-visit banner with Accept all / Reject / Customize; persistent re-open via footer
CHG-013 | 2. Global UI | Global Privacy Control (GPC) detection | P0 | Not Started | Lovable | CHG-001 | Server + client GPC detection; auto-opt-out of sale/share; consent record
CHG-014 | 2. Global UI | Service Area gate (CA/TX/FL only) | P0 | Not Started | Lovable | CHG-010 | Block out-of-state signups with waitlist modal
CHG-021 | 3. Legal Pages | /legal/terms route | P0 | Not Started | Lovable | CHG-002 | Render Terms of Service v2.0 from legal_documents table
CHG-022 | 3. Legal Pages | /legal/privacy route | P0 | Not Started | Lovable | CHG-002 | Render Privacy Policy v2.0
CHG-023 | 3. Legal Pages | /legal/cookies route | P0 | Not Started | Lovable | CHG-002 | Render Cookie Policy v2.0 with re-open banner button
CHG-024 | 3. Legal Pages | /legal/aup route | P0 | Not Started | Lovable | CHG-002 | Render Acceptable Use Policy v2.0
CHG-025 | 3. Legal Pages | /legal/cancellation route | P0 | Not Started | Lovable | CHG-002 | Render Cancellation Policy v2.0
CHG-026 | 3. Legal Pages | /legal/pro-agreement route | P0 | Not Started | Lovable | CHG-002 | Render Pro IC Agreement v2.0 (auth-gated)
CHG-027 | 3. Legal Pages | /legal/fcra route | P0 | Not Started | Lovable | CHG-002 | Render FCRA Disclosure v2.0 (reference only; signup uses standalone)
CHG-028 | 3. Legal Pages | /legal/sms-consent route | P0 | Not Started | Lovable | CHG-002 | Render SMS/TCPA Consent Disclosure v2.0
CHG-029 | 3. Legal Pages | /legal/accessibility route | P0 | Not Started | Lovable | CHG-002 | Render Accessibility Statement v2.0 with feedback form
CHG-030 | 3. Legal Pages | /legal/dmca route | P1 | Not Started | Lovable | CHG-002 | DMCA Designated Agent info + takedown form + counter-notice form
CHG-031 | 4. Client Signup | Client signup page structure | P0 | Not Started | Lovable | CHG-001, CHG-003, CHG-014 | Multi-step: account/profile/consent/confirmation; 3 req + 2 opt checkboxes
CHG-032 | 4. Client Signup | OFAC/sanctions screening on signup | P0 | Not Started | Lovable | CHG-003 | Run OFAC SDN check after profile, before consent; flag hits for manual review
CHG-033 | 4. Client Signup | Email verification flow | P0 | Not Started | Lovable | — | Standard email verification via Supabase Auth
CHG-041 | 5. Pro Signup | Pro signup overall structure (11 steps) | P0 | Not Started | Lovable | CHG-004, CHG-005 | 11-step flow; cannot skip steps; progress indicator
CHG-042 | 5. Pro Signup | Step 1: Account | P0 | Not Started | Lovable | CHG-041 | Email + password + basic profile
CHG-043 | 5. Pro Signup | Step 2: Profile | P0 | Not Started | Lovable | CHG-041 | Address, service area, photo, business name
CHG-044 | 5. Pro Signup | Step 3: Standard ToS Consent | P0 | Not Started | Lovable | CHG-041 | Three checkboxes — ToS+AUP+Cancellation, Privacy, Transactional comms
CHG-045 | 5. Pro Signup | Step 4: Pro IC Agreement (STANDALONE) | P0 | Not Started | Lovable | CHG-041, CHG-026 | Separate page; full agreement text; typed signature
CHG-046 | 5. Pro Signup | Step 5: STANDALONE FCRA Disclosure ★ CRITICAL ★ | P0 | Not Started | Lovable | CHG-041, CHG-027 | GILBERG COMPLIANT: own page, no other content, no other consent on page
CHG-047 | 5. Pro Signup | Step 6: SMS Consent (Two-Tier) | P0 | Not Started | Lovable | CHG-041, CHG-006 | Transactional (required) + Marketing (optional, separate checkbox)
CHG-048 | 5. Pro Signup | Step 7: Credentials Upload | P0 | Not Started | Lovable | CHG-041, CHG-004 | Business license OR EIN OR COI; CGL min $300k/$1M aggregate
CHG-049 | 5. Pro Signup | Step 8: Stripe Connect Express onboarding | P0 | Not Started | Lovable | CHG-041 | Embed Stripe hosted onboarding; store stripe_account_id
CHG-050 | 5. Pro Signup | Step 9: Submit to Checkr | P0 | Not Started | Lovable | CHG-041, CHG-005, CHG-046 | Create candidate + report; store IDs; webhook handler ready
CHG-051 | 5. Pro Signup | Step 10: Identity Verification | P0 | Not Started | Lovable | CHG-041 | Stripe Identity or Persona ID + selfie + liveness
CHG-052 | 5. Pro Signup | Step 11: Complete & Pending Review | P0 | Not Started | Lovable | CHG-041 | Welcome screen showing all pending verification checks
CHG-061 | 6. Booking Flow | Booking creation: Client side | P0 | Not Started | Lovable | CHG-081 | Property details, scope, MANDATORY hazard disclosure, recording disclosure, fee transparency
CHG-062 | 6. Booking Flow | Booking acceptance: Pro side | P0 | Not Started | Lovable | CHG-061 | Accept/Decline with full hazard visibility; no penalty for declines
CHG-063 | 6. Booking Flow | Subcontractor / Substitute flow | P1 | Not Started | Lovable | CHG-041 | Substitute Pro must be registered, screened, 18+; Client notified with cancel option
CHG-064 | 6. Booking Flow | Reliability Indicator | P2 | Not Started | Lovable | CHG-061 | Neutral signals only; never affects payouts or eligibility; excludes decline rate
CHG-081 | 7. Payment | Stripe Connect platform setup | P0 | Not Started | Nathan | — | Activate Connect Express; configure application fee; payouts schedule
CHG-082 | 7. Payment | Booking charge flow | P0 | Not Started | Lovable | CHG-081 | PaymentIntent with application_fee_amount + transfer_data; no PureTask balance
CHG-083 | 7. Payment | Review Window and auto-release | P0 | Not Started | Lovable | CHG-082 | 24-hour timer; auto-release on expiry; idempotent cron
CHG-084 | 7. Payment | Tipping flow | P1 | Not Started | Lovable | CHG-082 | 100% to Pro minus Stripe fee; PureTask retains $0
CHG-085 | 7. Payment | Pro payout dashboard | P1 | Not Started | Lovable | CHG-049 | Embed or link Stripe Express dashboard
CHG-096 | 8. Cancellation | Client cancellation flow (6h/2h/<2h) | P0 | Not Started | Lovable | CHG-082 | Time-based fee logic; show fee modal before confirm
CHG-097 | 8. Cancellation | Pro cancellation flow | P0 | Not Started | Lovable | CHG-082 | Refund + free re-book + service credit logic; no-show suspension trigger
CHG-098 | 8. Cancellation | Booking modification flow | P1 | Not Started | Lovable | CHG-082 | Reschedule, scope change, address change with recalculation
CHG-099 | 8. Cancellation | Recurring Booking management | P1 | Not Started | Lovable | CHG-082 | Per-instance cancel; entire schedule cancel; substitute Pro flow
CHG-100 | 8. Cancellation | Partial completion handling | P1 | Not Started | Lovable | CHG-082 | ≥75% full pay / 25-75% pro-rata / <25% trip fee
CHG-101 | 8. Cancellation | Dispute flow | P0 | Not Started | Lovable | CHG-082 | Open within Review Window; evidence upload; freeze funds; admin mediation 5 days
CHG-111 | 9. Account Settings | Account settings landing page | P0 | Not Started | Lovable | CHG-003 | Tabs: Profile, Notifications, Privacy, Payment, Security, Close
CHG-112 | 9. Account Settings | Notification preferences page | P0 | Not Started | Lovable | CHG-006, CHG-111 | Email/SMS/Push toggles; SMS marketing requires re-acknowledging TCPA Express Written Consent
CHG-113 | 9. Account Settings | Privacy page / CCPA controls | P0 | Not Started | Lovable | CHG-001, CHG-013, CHG-111 | Do Not Sell, Limit SPI, DSR request form (45-day SLA), Shine the Light
CHG-114 | 9. Account Settings | Do Not Sell or Share public page | P0 | Not Started | Lovable | CHG-001 | Public route /privacy/do-not-sell linked from footer
CHG-115 | 9. Account Settings | Limit Use of SPI public page | P0 | Not Started | Lovable | CHG-001 | Public route /privacy/limit-spi linked from footer
CHG-116 | 9. Account Settings | Account closure flow | P0 | Not Started | Lovable | CHG-003 | Modal with retention warning; cancel pending Bookings; schedule purge
CHG-117 | 9. Account Settings | Arbitration opt-out flow (30 days) | P1 | Not Started | Lovable | CHG-003 | 30-day window from account_created_at; one-time opt-out; consent record
CHG-131 | 10. SMS Logic | SMS sending wrapper with consent + quiet-hour check | P0 | Not Started | Lovable | CHG-006, CHG-010 | Every SMS gated by consent + TCPA quiet hours + Florida FTSA + sender ID
CHG-132 | 10. SMS Logic | STOP / HELP keyword handler | P0 | Not Started | Lovable | CHG-131 | Twilio inbound webhook; STOP revokes; HELP responds; START resubscribes
CHG-133 | 10. SMS Logic | Right to access consent record | P1 | Not Started | Lovable | CHG-006 | User can request consent history; PDF export within 30 days
CHG-146 | 11. Trust & Safety | Checkr webhook handler | P0 | Not Started | Lovable | CHG-005, CHG-050 | Process report.completed, consider, suspended, disputed events
CHG-147 | 11. Trust & Safety | Individualized Assessment workflow (CA Fair Chance Act) | P0 | Not Started | Nathan+Lovable | CHG-146 | Admin review w/ Fair Chance Act exclusions documented in DB
CHG-148 | 11. Trust & Safety | Pre-Adverse Action Notice send | P0 | Not Started | Lovable | CHG-147 | Generate from Doc 07A template; 5-business-day wait; applicant response form
CHG-149 | 11. Trust & Safety | Adverse Action Notice send | P0 | Not Started | Lovable | CHG-148 | Generate from Doc 07B template; 5-year retention of records
CHG-150 | 11. Trust & Safety | Ongoing background check rechecks | P1 | Not Started | Lovable | CHG-146 | Daily cron; submit annual rechecks; continuous monitoring alerts
CHG-151 | 11. Trust & Safety | AUP violation reporting | P1 | Not Started | Lovable | CHG-007 | /help/report form; admin queue; 48hr response; anti-retaliation
CHG-152 | 11. Trust & Safety | Appeal flow for suspensions/terminations | P1 | Not Started | Lovable | CHG-003 | Independent reviewer; 30-day SLA; decision final
CHG-161 | 12. Reviews | Review submission | P1 | Not Started | Lovable | CHG-061 | Client-only post-completion; no edits after; Pro one response; anti-retaliation tracking
CHG-171 | 13. Accessibility | Semantic HTML audit | P1 | Not Started | Lovable | — | Proper header/nav/main/article/footer; heading order; lists for lists; buttons for buttons
CHG-172 | 13. Accessibility | Keyboard navigation | P1 | Not Started | Lovable | — | Tab access to every interactive element; visible focus; skip-to-content link
CHG-173 | 13. Accessibility | ARIA labels and landmarks | P1 | Not Started | Lovable | — | Icon-only buttons labeled; landmarks where needed
CHG-174 | 13. Accessibility | Color contrast (4.5:1 AA) | P1 | Not Started | Lovable | — | All text meets 4.5:1; verified with axe DevTools
CHG-175 | 13. Accessibility | Form labels | P1 | Not Started | Lovable | — | Every input has label; required fields aria-required; errors aria-live polite
CHG-176 | 13. Accessibility | Reduced motion | P1 | Not Started | Lovable | — | Respect prefers-reduced-motion; disable autoplay, parallax, page transitions
CHG-177 | 13. Accessibility | Alternative format request | P2 | Not Started | Lovable | — | /help/accessibility form; 10-business-day SLA; routes to accessibility@puretask.co
CHG-186 | 14. Mobile | iOS app: Apple-specific terms display | P0 | Not Started | Lovable | CHG-021 | Doc 01 Section 19.1 verbatim in iOS app ToS view
CHG-187 | 14. Mobile | Android app: Google-specific terms display | P0 | Not Started | Lovable | CHG-021 | Doc 01 Section 19.2 verbatim in Android app ToS view
CHG-188 | 14. Mobile | iOS / Android push notification permission | P1 | Not Started | Lovable | — | OS-level permission prompt with clear copy; default OFF
CHG-189 | 14. Mobile | IDFA / AAID handling | P1 | Not Started | Lovable | — | Never collect for advertising without explicit opt-in
CHG-190 | 14. Mobile | App Tracking Transparency (iOS) | P1 | Not Started | Lovable | — | ATT prompt with clear purpose string; default no tracking
CHG-196 | 15. Admin | Admin dashboard | P1 | Not Started | Lovable | CHG-003 | Retool or custom: pending Pros, BG check queue, AUP reports, DSR queue, disputes
CHG-197 | 15. Admin | Data Subject Rights (DSR) request handling | P0 | Not Started | Lovable | CHG-113 | Queue + workflows for Know, Delete, Correct, Portability, Opt-out, Appeal; 45-day SLA
CHG-198 | 15. Admin | Privacy request audit trail | P0 | Not Started | Lovable | CHG-007, CHG-197 | Every DSR logged; 4-year retention
CHG-199 | 15. Admin | Compliance calendar / reminders | P2 | Not Started | Nathan | — | FTB $800, CA Stmt of Info, insurance renewals, trademark, DPA renewals, 1099-K
CHG-200 | 15. Admin | Incident response runbook integration | P1 | Not Started | Nathan+Lovable | — | On-call, forensics, notification windows by state (30/45/60 days)
CHG-201 | 15. Admin | DMCA Designated Agent registration | P1 | Not Started | Nathan | — | Register at dmca.copyright.gov ($6); update Doc 01 Section 14.3

## Session Plan
Lovable Session Implementation Plan
Each Lovable session implements a focused chunk of CHG items
Session # | Theme | CHG Items | Target Week | Status
Session 1 | Foundation + Global UI | CHG-001 to CHG-014 | Week 1 | Not Started
Session 2 | Legal Pages | CHG-021 to CHG-030 | Week 1-2 | Not Started
Session 3 | Client Signup | CHG-031 to CHG-033 | Week 2 | Not Started
Session 4 | Pro Signup (CRITICAL — Standalone FCRA) | CHG-041 to CHG-052 | Week 2-3 | Not Started
Session 5 | Payment & Booking | CHG-061 to CHG-064, CHG-081 to CHG-085, CHG-096 to CHG-101 | Week 3-4 | Not Started
Session 6 | Trust, Safety, SMS | CHG-131 to CHG-152 | Week 4-5 | Not Started
Session 7 | Account Settings & Privacy | CHG-111 to CHG-117 | Week 5 | Not Started
Session 8 | Accessibility, Mobile, Admin | CHG-161, CHG-171 to CHG-201 | Week 5-6 | Not Started

## Reference
Reference: Status, Priority, Owner Definitions
STATUS
Not Started | No work begun. Default state.
In Progress | Implementation underway. Date Started populated.
Blocked | Cannot proceed until a dependency or external decision resolves. Document in Blocker column.
Done | Implementation complete per Acceptance Notes. Date Completed populated. Awaiting verification.
Verified | Manually verified by Nathan against full Acceptance Criteria in Doc 15. Date Verified populated. SHIPPABLE.
PRIORITY
P0 | Blocker. Cannot launch publicly without this. Most are legal/compliance critical.
P1 | Required before public launch. Cannot defer beyond Phase 6 of Doc 12 launch checklist.
P2 | Should ship within 30 days of public launch. Defer-able for soft launch only.
P3 | Nice-to-have. Roadmap. No launch dependency.
OWNER
Lovable | Pure software implementation Lovable AI can do (UI, schema, business logic).
Nathan | Manual / operational work requiring real-world action (file LLC, buy insurance, register accounts).
Nathan+Lovable | Lovable can scaffold but Nathan must complete (e.g., vendor account setup + integration).
Attorney | Outside legal counsel.
Vendor | Third-party vendor (Stripe, Checkr, Twilio, OneSignal, etc.).
— | No specific owner; environmental setup.