Table of Contents

# PureTask — Operational Launch Checklist

Document 12 Version: 1.0

This is the sequenced operational plan for getting PureTask from current state (sole proprietorship, no LLC, no live platform) to first paid Booking with full legal, financial, technical, and operational readiness.

The plan is structured as 6 phases spanning approximately 8–12 weeks. Each phase has hard dependencies on the prior phase. Some work within a phase can run in parallel (noted as “Track A / Track B”). Treat this like a Gantt chart — boxes don’t move unless their dependencies are clear.

Critical-path items are marked with 🚨. Slipping these slips the launch.

## At-a-Glance Timeline

| Phase | Duration | Focus | Gate to Next Phase |
| --- | --- | --- | --- |
| Phase 1 | Week 1–2 | Entity formation | LLC formed; EIN obtained |
| Phase 2 | Week 2–4 | Banking, insurance, vendor accounts | Business bank account live; insurance bound |
| Phase 3 | Week 3–6 | Tech infrastructure | App + Stripe Connect Express operational |
| Phase 4 | Week 4–6 | Legal document execution | All vendor DPAs signed; ToS/Privacy/etc. published |
| Phase 5 | Week 6–8 | Pilot / soft launch | ≥5 successful Bookings completed without incident |
| Phase 6 | Week 8+ | Public launch | Marketing live; SMS/email infrastructure registered |

## Phase 1 — Entity Formation (Week 1–2)

Goal: Move PureTask from sole proprietorship to a California LLC with separate legal existence.

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 1.1 | 🚨 Engage California business attorney for 1-hour consultation on LLC formation specifics. | None | 1 wk | Nathan | $300–800 |
| 1.2 | 🚨 File Form LLC-1 Articles of Organization with California Secretary of State (bizfileonline.sos.ca.gov). | 1.1 | 1 day | Nathan | $70 |
| 1.3 | Reserve and verify the registered agent (self-serve as Nathan, or hire a registered agent service like Northwest, ZenBusiness, Wolters Kluwer). | 1.2 | 1 day | Nathan | $0 (self) / $125–300/yr |
| 1.4 | 🚨 Adopt the Operating Agreement (Doc 09) by executing as sole member. Retain in business records — do not file with SOS. | 1.2 | 1 day | Nathan | $0 |
| 1.5 | 🚨 Apply for EIN from IRS (irs.gov; free; online; ~10 minutes). | 1.2 | 1 day | Nathan | $0 |
| 1.6 | File Form LLC-12 Statement of Information with California SOS within 90 days of formation. | 1.2 | 1 day | Nathan | $20 |
| 1.7 | Pay $800 California annual franchise tax (FTB Form 3522) by the 15th day of the 4th month after formation. | 1.5 | 1 day | Nathan | $800 |
| 1.8 | Register for Texas and Florida foreign qualification when ready to onboard Pros/Clients in those states (defer until Phase 6 unless launching simultaneously). | Pre-launch | 2 wk | Nathan | $750–1,200/state |
| 1.9 | Record formation documents in secure cloud + offsite backup. | 1.2–1.6 | 1 day | Nathan | $0 |

Phase 1 Exit Criteria: - ✅ LLC-1 filing confirmation in hand - ✅ EIN letter (CP 575) in hand - ✅ Operating Agreement signed - ✅ All formation documents stored securely with backup

## Phase 2 — Banking, Insurance, Vendor Accounts (Week 2–4)

Goal: Establish the financial and operational infrastructure of PureTask LLC, separate from Nathan’s personal accounts.

### Track A — Banking & Finance

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 2A.1 | 🚨 Open business checking account in PureTask LLC’s name (recommended: Mercury, Relay, Bluevine, or local credit union). Bring: Articles of Organization, EIN letter, Operating Agreement. | 1.2, 1.5, 1.4 | 1 wk | Nathan | $0–$15/mo |
| 2A.2 | Open business credit card in PureTask LLC’s name (Chase Ink Cash, Amex Business Cash, Capital One Spark). | 2A.1 | 1 wk | Nathan | $0/yr most cards |
| 2A.3 | Set up business bookkeeping software (QuickBooks, Wave, or Bench). Connect to business bank + credit card. | 2A.1, 2A.2 | 2 days | Nathan | $0–$80/mo |
| 2A.4 | Engage a CPA or bookkeeper for quarterly tax estimates and annual filing. | 2A.3 | 1 wk | Nathan | $500–2,000/yr |

### Track B — Insurance

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 2B.1 | 🚨 Obtain Commercial General Liability (CGL) policy for PureTask LLC. Minimum $1M / $2M. | 1.2 | 1–2 wk | Nathan | $500–2,000/yr |
| 2B.2 | 🚨 Obtain Technology Errors & Omissions / Cyber Liability policy. Minimum $1M. | 1.2 | 1–2 wk | Nathan | $1,000–3,000/yr |
| 2B.3 | Obtain Umbrella Liability policy (excess coverage). $1M+ | 2B.1 | 1 wk | Nathan | $300–700/yr |
| 2B.4 | Confirm personal homeowner’s / renter’s insurance does not exclude business activities; add rider if needed. | None | 1 wk | Nathan | $0–$200/yr |

### Track C — Business Identity & Communications

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 2C.1 | Register dedicated business email (e.g., legal@puretask.co, support@puretask.co, dmca@puretask.co). Currently using otherpuretask@gmail.com — migrate before public launch. | None | 1 day | Nathan | $6–18/user/mo (Google Workspace) |
| 2C.2 | Obtain dedicated business phone number (Google Voice for free, or a VoIP like Grasshopper / OpenPhone). | None | 1 day | Nathan | $0–$30/mo |
| 2C.3 | Register PureTask trademark with USPTO (Word mark “PureTask”; design mark for Dash mascot). | None | 8–12 mo | Nathan + IP attorney | $250–350/class + attorney $500–1,500 |
| 2C.4 | File DMCA Designated Agent registration with U.S. Copyright Office (dmca.copyright.gov). | 2C.1 | 1 day | Nathan | $6 |

Phase 2 Exit Criteria: - ✅ Business checking account active and funded with seed capital - ✅ Business credit card issued - ✅ CGL + Tech E&O policies bound, certificates of insurance in hand - ✅ Dedicated business email in use for legal communications - ✅ DMCA Designated Agent registered

## Phase 3 — Tech Infrastructure (Week 3–6, overlaps with Phase 2)

Goal: Build, configure, and security-harden the technical platform with Stripe Connect Express as the payment spine.

### Track A — Core Platform

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 3A.1 | Finalize Supabase project (auth, database, row-level security). | None | 1 wk | Nathan | $0–$25/mo |
| 3A.2 | Implement RLS policies for every table containing PII, with explicit deny-by-default and role-based grants. | 3A.1 | 1 wk | Nathan | — |
| 3A.3 | Implement encryption at rest for sensitive fields (last 4 of SSN/Tax ID, government-ID images, precise geolocation). | 3A.1 | 1 wk | Nathan | — |
| 3A.4 | Implement audit logging of all access to PII (who, what, when). | 3A.2 | 3 days | Nathan | — |
| 3A.5 | Build clickwrap acceptance flow for ToS, Privacy Policy, AUP, SMS, and FCRA Disclosure (separate FCRA standalone). Each clickwrap records: timestamp, IP, exact text accepted, checkbox state, version of document, user ID. Retain 5+ years. | 3A.1 | 1 wk | Nathan | — |
| 3A.6 | Build Pro signup flow with FCRA standalone disclosure page (Doc 07) and Pro IC Agreement clickwrap (Doc 06) as distinct, separate signing steps. | 3A.5 | 1 wk | Nathan | — |

### Track B — Stripe Connect Express

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 3B.1 | 🚨 Create Stripe account in PureTask LLC’s name (using EIN, not Nathan’s SSN). | 1.5 | 1 day | Nathan | $0 |
| 3B.2 | 🚨 Activate Stripe Connect platform (Express accounts). | 3B.1 | 2 days | Nathan | — |
| 3B.3 | Implement Pro onboarding into Stripe Express (KYC flow). Each Pro creates own Stripe Express account. | 3B.2, 3A.6 | 1 wk | Nathan | — |
| 3B.4 | Implement payment flow: Client charge → funds held in Stripe → Review Window → release to Pro Express account minus application fee. | 3B.3 | 2 wk | Nathan | — |
| 3B.5 | Implement tip flow: post-completion add-on, 100% to Pro minus Stripe fees. | 3B.4 | 3 days | Nathan | — |
| 3B.6 | Test chargeback handling, dispute mediation, and payout failure scenarios in Stripe test mode. | 3B.4 | 1 wk | Nathan | — |
| 3B.7 | Confirm agent-of-payee documentation in place and Stripe contract acknowledges PureTask as marketplace, not money transmitter. | 3B.1, Doc 06, Doc 01 | 1 wk | Nathan + attorney | — |

### Track C — Trust & Safety Vendors

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 3C.1 | 🚨 Engage background-check vendor (Checkr recommended for marketplace UX). | 1.2, 1.5 | 1 wk | Nathan | Per-check $25–75 |
| 3C.2 | 🚨 Use Checkr’s standalone FCRA disclosure form for the actual production form (not Doc 07 verbatim — Doc 07 is the template/template). Confirm Checkr form includes California ICRAA + Fair Chance Act + AB 2188 protections. | 3C.1 | 1 wk | Nathan + attorney | — |
| 3C.3 | Set up Pre-Adverse Action Notice (Doc 07A) and Adverse Action Notice (Doc 07B) templates in Checkr (or via your own workflow). 5-business-day pre-adverse wait window. | 3C.2 | 1 wk | Nathan | — |
| 3C.4 | Configure Checkr ongoing rechecks (annual) and continuous monitoring of criminal history. | 3C.2 | 3 days | Nathan | Per-check |
| 3C.5 | Engage identity-verification sub-vendor (Stripe Identity or Persona for ID document verification + face match). | 3B.1 | 1 wk | Nathan | $1–2 per verification |

### Track D — Comms & Notifications

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 3D.1 | 🚨 Register PureTask brand with The Campaign Registry (TCR) for 10DLC SMS sending. | 1.2, 1.5 | 1 wk | Nathan | $4 brand + $10/campaign |
| 3D.2 | Provision Twilio (or alternative) account, link to TCR-registered campaign for transactional SMS. | 3D.1 | 1 wk | Nathan | $0.0075/SMS |
| 3D.3 | Build two-tier SMS consent flow (transactional vs marketing) per Doc 08. Marketing requires affirmative checkbox. | 3A.5 | 1 wk | Nathan | — |
| 3D.4 | Implement STOP / HELP keyword handling and consent-record retention. | 3D.3 | 3 days | Nathan | — |
| 3D.5 | Configure TCPA quiet hours (8am–9pm local) and Florida FTSA quiet hours (8am–8pm, no Sunday) for marketing SMS. | 3D.3 | 3 days | Nathan | — |
| 3D.6 | Configure transactional email (SendGrid, Postmark, Resend). Set up SPF, DKIM, DMARC for puretask.co. | 2C.1 | 1 wk | Nathan | $0–$20/mo |
| 3D.7 | Configure OneSignal for push notifications (iOS + Android). | 3A.1 | 3 days | Nathan | $0 free tier |

### Track E — Cookies, Privacy, Accessibility

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 3E.1 | Implement cookie banner with explicit categories (essential, functional, analytics, advertising) and a persistent Preferences link. | 3A.1 | 1 wk | Nathan | $0 (self) / $50/mo (Cookiebot/Osano) |
| 3E.2 | Honor Global Privacy Control (GPC) as an opt-out of sale/share. | 3E.1 | 2 days | Nathan | — |
| 3E.3 | Implement CCPA/CPRA opt-out flow (“Do Not Sell or Share My Personal Information”; “Limit Use of My Sensitive Personal Information”). Both linked in footer. | 3A.1 | 1 wk | Nathan | — |
| 3E.4 | Engage accessibility auditor (Deque, Level Access, or freelance) for WCAG 2.1 AA baseline audit. Update Accessibility Statement (Doc 10) with results. | 3A.1 | 2 wk | Nathan | $2,000–5,000 |
| 3E.5 | Remediate critical accessibility findings before public launch. | 3E.4 | 2–4 wk | Nathan | — |

Phase 3 Exit Criteria: - ✅ Platform builds, deploys, and runs in staging - ✅ Stripe Connect Express payments succeed in test mode - ✅ Pro onboarding (signup + FCRA + Pro IC Agreement) flows end-to-end - ✅ Background check + identity verification succeed for test Pro - ✅ SMS sends from registered 10DLC - ✅ Cookie banner and GPC honoring confirmed via manual test - ✅ Initial accessibility audit complete

## Phase 4 — Legal Document Execution (Week 4–6)

Goal: Execute all platform agreements in the LLC’s name. Without this, the documents have no legal effect for the LLC.

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 4.1 | 🚨 Engage California gig-economy attorney for 2-hour review of: ToS, Pro IC Agreement, AUP, Cancellation Policy. Focus: ABC test exposure. | 1.2 | 2 wk | Nathan | $1,500–3,000 |
| 4.2 | 🚨 Engage California consumer-tech attorney for review of: Privacy Policy, Cookie Policy, FCRA Disclosure, SMS Consent, DPA template. | 1.2 | 2 wk | Nathan | $3,000–6,000 |
| 4.3 | Incorporate attorney edits into all 11 documents (and 07A/07B). | 4.1, 4.2 | 1 wk | Nathan | — |
| 4.4 | Re-execute every Platform document in PureTask LLC’s legal name (not Nathan d/b/a). | 4.3 | 3 days | Nathan | — |
| 4.5 | 🚨 Sign Stripe Connect Platform Agreement (Stripe’s form) and Stripe DPA in PureTask LLC’s name. | 3B.1 | 1 wk | Nathan | — |
| 4.6 | 🚨 Sign Supabase DPA in PureTask LLC’s name. Use Doc 11 as comparison. | 3A.1 | 1 wk | Nathan | — |
| 4.7 | Sign OneSignal DPA in PureTask LLC’s name. | 3D.7 | 3 days | Nathan | — |
| 4.8 | Sign Twilio DPA (and TCR Brand Acknowledgment) in PureTask LLC’s name. | 3D.2 | 3 days | Nathan | — |
| 4.9 | 🚨 Sign Checkr Master Services Agreement and DPA in PureTask LLC’s name. | 3C.1 | 1 wk | Nathan | — |
| 4.10 | Sign DPAs with all other material vendors (email provider, hosting, analytics). | 3D.6 | 1 wk | Nathan | — |
| 4.11 | Publish all final legal documents at /legal/* URLs. Confirm links work in app and email templates. | 4.4 | 3 days | Nathan | — |
| 4.12 | Update Privacy Policy effective date and ToS effective date for launch day. | 4.11 | 1 day | Nathan | — |

Phase 4 Exit Criteria: - ✅ All 11+ documents reviewed by attorneys, edits incorporated - ✅ All documents executed in PureTask LLC name - ✅ All vendor DPAs signed - ✅ Published documents linked correctly in app

## Phase 5 — Pilot / Soft Launch (Week 6–8)

Goal: Validate end-to-end Booking flow with real (but limited) Users. Identify and resolve issues before public launch.

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Recruit 5–10 friendly Pros (recommended: existing acquaintances who clean professionally; offer waived Platform Fee for pilot period). | Phases 3, 4 | 1 wk | Nathan | $0 (waived fees) |
| 5.2 | Pilot Pros complete full signup: ToS, Privacy, Pro IC Agreement, FCRA Disclosure, SMS Consent, Stripe Express KYC, background check, identity verification. | 5.1 | 2 wk | Pros | $25–75/Pro for BG check |
| 5.3 | Recruit 5–10 friendly Clients for pilot Bookings. | Phases 3, 4 | 1 wk | Nathan | $0 |
| 5.4 | Complete at least 5 end-to-end Bookings without major incident. Test: cancellation flow, dispute flow, tipping, chargeback simulation. | 5.2, 5.3 | 2 wk | Pilot Users | Revenue offset |
| 5.5 | Collect pilot feedback. Bug triage. Fix critical issues. | 5.4 | 1 wk | Nathan | — |
| 5.6 | Pilot retrospective. Document issues, owner sign-off on each. | 5.4 | 2 days | Nathan | — |
| 5.7 | Conduct second accessibility audit if first audit flagged issues. | 3E.5 | 1 wk | Auditor | $1,000–2,000 |
| 5.8 | Conduct security review of production environment. Penetration test optional but recommended. | Phase 3 | 1 wk | Nathan + optional consultant | $0–5,000 |

Phase 5 Exit Criteria: - ✅ ≥5 Bookings completed without incident - ✅ No critical bugs outstanding - ✅ Accessibility audit findings remediated - ✅ Security review complete

## Phase 6 — Public Launch (Week 8+)

Goal: Open the Platform to the general public in target markets, with marketing infrastructure live.

| # | Task | Dependency | Time | Owner | Cost |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Define launch market (recommended: start with Sacramento County, expand to Bay Area, then to Texas (Austin/Houston) and Florida (Miami/Orlando) as Pro density permits). | Phase 5 | 1 wk | Nathan | $0 |
| 6.2 | 🚨 If launching in Texas or Florida: file foreign qualification with each state’s SOS. | 1.8 | 2 wk | Nathan | $750–1,200/state |
| 6.3 | Confirm insurance covers operations in Texas and Florida (most CGL policies do automatically; verify with broker). | 2B.1 | 1 wk | Nathan | — |
| 6.4 | Launch landing page at puretask.co with clear value propositions, sign-up CTAs, and links to all legal documents. | Phase 4 | 1 wk | Nathan | — |
| 6.5 | Set up Google Business Profile for PureTask LLC. | 2C.1 | 3 days | Nathan | $0 |
| 6.6 | Launch paid acquisition carefully — start with $20–50/day budgets on Google Ads + Meta Ads in Sacramento ZIP codes. | 6.4 | Ongoing | Nathan | $600–1,500/mo to start |
| 6.7 | Implement referral program (per CCPA Notice of Financial Incentives in Doc 02 Section 15). | 6.4 | 1 wk | Nathan | $0 |
| 6.8 | Launch press / community outreach: Reddit local subs, Nextdoor, local Facebook groups. Avoid spam — engage authentically. | 6.4 | Ongoing | Nathan | $0 |
| 6.9 | Set up monitoring dashboards for: signup funnel, Booking completion rate, dispute rate, payment failure rate, support response time. | Phase 3 | 1 wk | Nathan | $0–$50/mo |
| 6.10 | Set up customer support intake (email + in-app + optional Intercom/Crisp). | 2C.1 | 1 wk | Nathan | $0–$80/mo |

Phase 6 Exit Criteria: - ✅ First public sign-up - ✅ First paid Booking from an organic User (not pilot) - ✅ Marketing channels active - ✅ Monitoring + support live

## Dependency Map (Critical Path)

1.2 (LLC-1)  ─┬─► 1.4 (Op Agt) ─┬─► 1.5 (EIN) ─┬─► 2A.1 (Bank)
              │                  │              │
              │                  │              ├─► 2B.1, 2B.2 (Insurance)
              │                  │              │
              │                  │              ├─► 2C.4 (DMCA Agent)
              │                  │              │
              │                  │              ├─► 3B.1 (Stripe)
              │                  │              │
              │                  │              ├─► 3C.1 (Checkr)
              │                  │              │
              │                  │              └─► 3D.1 (TCR/SMS)
              │
              ├─► 1.6 (Stmt of Info)
              │
              └─► 1.7 ($800 FTB)

Phase 3 (build) ── runs in parallel with Phase 2 once 1.2/1.4/1.5 done

Phase 4 (legal execution) ── blocks on (Phase 1 + Phase 2 banking + Phase 3 tech) ── critical path through 4.1, 4.2, 4.5

Phase 5 (pilot) ── blocks on (Phase 4 execution + Phase 3 tech) — gate to Phase 6

Phase 6 (public launch) ── only after Phase 5 exit criteria met

## Estimated Total Cost (Phase 1 through Phase 6)

| Category | Estimated Range |
| --- | --- |
| State filing fees (CA + foreign qual TX/FL) | $1,800–$3,000 |
| First year CA franchise tax | $800 |
| Attorneys (gig-economy + consumer-tech) | $4,500–$9,000 |
| Insurance (CGL + Tech E&O + Umbrella, year 1) | $2,000–$5,000 |
| Trademark registration (Word + Design) | $750–$2,000 |
| Background-check + identity verification (first 100 Pros) | $2,500–$7,500 |
| Stripe + SMS + email + hosting (first 6 months) | $500–$2,000 |
| Accessibility audit | $2,000–$5,000 |
| Security review (optional) | $0–$5,000 |
| Marketing budget (3-month pilot) | $1,800–$4,500 |
| Total to first paid Booking | $16,650–$43,000 |

This is a budget estimate. Actual costs vary depending on your appetite for legal review, marketing spend, and security investment. Reduce by deferring trademark registration, foreign qualification, and aggressive marketing; increase by adding penetration testing, multi-state launch at once, and stronger insurance.

## Risk Register (Top 5 to Track Throughout)

| # | Risk | Mitigation |
| --- | --- | --- |
| 1 | California ABC test reclassification of Pros as employees. | Pro IC Agreement, IC-friendly UX, attorney consultation, eventual TX/FL revenue dilution. |
| 2 | Money transmitter / escheat exposure from holding User funds. | Stripe Connect Express with proper application-fee architecture; no PureTask-held balances; agent-of-payee documentation. |
| 3 | FCRA / TCPA / CCPA class-action. | Standalone FCRA disclosure (Gilberg), two-tier SMS consent, opt-out flows, GPC honoring, attorney review. |
| 4 | Background-check gap leading to bad-actor Pro. | Checkr + identity verification + continuous monitoring; clear suspension protocols in AUP; insurance. |
| 5 | Veil-piercing if commingling continues. | Strict separation of LLC accounts, business-name signage everywhere, Operating Agreement Appendix A hygiene checklist. |

## Owner Sign-Off

When each phase is complete, Nathan signs and dates:

| Phase | Sign-Off | Date |
| --- | --- | --- |
| Phase 1 — Entity Formation | _____________________________ | __________ |
| Phase 2 — Banking, Insurance, Vendors | _____________________________ | __________ |
| Phase 3 — Tech Infrastructure | _____________________________ | __________ |
| Phase 4 — Legal Document Execution | _____________________________ | __________ |
| Phase 5 — Pilot / Soft Launch | _____________________________ | __________ |
| Phase 6 — Public Launch | _____________________________ | __________ |

This is an operational planning document, not legal advice. Engage attorneys, accountants, and insurance brokers at the points indicated. Numbers and timelines are estimates and will vary by individual circumstances.